## Sheet1
Application | No. | Obstacle | Type | Proposed solution | Initiation Date | Estimated completion date | Completion date | Current status | Assigned to | Result
Inventory | 1 | Avoid duplication of items to ease the search process | Enhancement | Create Master item to unify item Code on all our inv org . Avoid any duplication of Same item . | 20/2/2025 | 20/2/2025 | 21/2/2025 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 2 | There are stagnant inventory items that remain unsold for a long period ,we need to stop purchasing this item | New Feature | Custom item status classify Phase-out , control transaction's Type will be performed on the item . | 20/2/2025 | 20/2/2025 | 21/2/2025 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 3 | We have a best seller item that can not be out of stock | New Feature | Enables MIN-MAX Planning to avoid the item to be out of stock, when the stock reach the minimum Qunatity, the system automatically reorder the item to reach the MAX Qunatity | 20/2/2025 | 20/2/2025 | 21/2/2025 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 4 | Each time we create a new item, we are required to fill nearly 380 attributes, resulting in significant time and effort | New Feature | Create item template and use it . | 20/2/2025 | 21/2/2025 | 21/2/2025 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 5 | Have existing item when needed to edit on is not being editable . | Enhancement | From item attribute control can edit on organization item and make Master item not editable . | 20/2/2025 | 21/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 6 | The employee in one store can access another store | Enhancement | Remove Employee Zamalek's responsibility from the organization access of the Montaza store . | 20/2/2025 | 22/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 7 | Want to buy or sell goods but we don’t have purchasing or order management application . | New Feature | From Inventory application can make issue and Receipt from Miscellonous Transaction . | 20/2/2025 | 22/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 8 | If Employee want to make an issue or receipt on different accounts number . | New Feature | From Miscellonous Transaction Source inventory , can enter a different account number and make it editable . | 20/2/2025 | 23/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 9 | If Employee want to make an issue or receipt on only account number . | New Feature | From Miscellonous Transaction Source Account, can enter only one account number that can't be editable . | 20/2/2025 | 23/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 10 | If Employee want to make issue or receipt on only one account number and hidden . | New Feature | From Miscellonous Transaction Source Account Alias, can enter only one account number in backgroung and make it hidden. | 20/2/2025 | 24/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 11 | The empolyee could write the account number wrongly which may affect data accuracy | New Feature | Create Customized Short Hand Alias: Instead of the empolyee writimg the number of the account, He writes the name of the Account that expresses the account number | 20/2/2025 | 24/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 12 | To see all transactions in detail | Enhancement | From Material Transaction can see all Transactions more detailed . | 20/2/2025 | 24/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 13 | We want transfer items from Warehouse to Store and vice versa | Enhancement | Create Shipping Network From store to another and make intransit transfer , its type intransit | 20/2/2025 | 24/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 14 | To distinguish group of items with a number , because if an iteam was found broken , we can know shipment received by who . | New Feature | Create a lot number on group of items . | 20/2/2025 | 25/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 15 | If we received a group of items from the supplier and want to distinguish between them | New Feature | Enables Across items Uniqueness lot number , Each group of items has a unique number. | 20/2/2025 | 25/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 16 | when receiving items , system will make lot number automatic and the user can’t edit it , this is mandatory . | New Feature | Enable organizational level Generation in lot control . | 20/2/2025 | 25/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 17 | at the end of the summer season , we withdraw the summer clothes in the store | Enhancement | create Expiration Date on lot group of items . | 20/2/2025 | 25/2/2025 | 2025-01-04 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 18 | To issue only the required quantity from a Lot group of items without the need to issue the entire lot at once | New Feature | Enables Lot Divisible on group of items . | 20/2/2025 | 25/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 19 | Having clothes of different colours , but they have the same cost . | New Feature | Allow checkbox item Revision on items to fix the cost on the different colours . | 20/2/2025 | 26/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 20 | If a requested item is unavailable in the current store but available in another store | Enhancement | Create Move Order Transfer, to transfer items to other store | 20/2/2025 | 27/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory | 21 | we make stocktaking every year to ensure that the quantity of items at the system equal the quantity at the stores ,if any transaction was made by any employee for thefts needs or by mistake to avoid loses to the inventory and for security purposes | Enhancement | Create Physical inventory : 1-create inventroy committee . 2-snapshot . 3-create tags when count item and put tag on it . 4-printing tags . 5-counting items . 6- return to inventory committee to receive item counting . 7-comparison between counting and on hand items . 8- detect tolerance and approving difference . | 20/2/2025 | 28/2/2025 | 2025-01-03 | Opened | Menna-Ali-Noran-David | Completed
Inventory |  |  |  | Create Physical inventory . 1-create inventroy committee . 2-snapshot . 3-create tags when count item and put tag on it . 4-printing tags . 5-counting items . 6- return to inventory committee to receive item counting . 7-comparison between counting and on hand items . 8- detect tolerance and approving difference . | 20/2/2026 | 28/2/2026 | 2025-01-04 | Opened | Menna-Ali-Noran-David | Completed